## Sheet1
Details as of May 28, 2024
Student | SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
Task | Understanding the mathematics behind the rotation of an image at any point | Implementing image rotation algorithm in halide | Effectively scheduling and parallelizing existing rotation algorithms
Task details/summary | 1. Analyzing and understanding the mathematics behind the rotation of an image at any point, better known as affine transformation. | 1. Implementing an image rotation algorithm in Halide using the warp affine function. | 1. It is claimed that the leading cause of slow image processing speeds is serialized computing, and leveraging parallel processing capabilities is thus the way to go.
| 2. In this method, we use the center of the image to get the new x and y coordinates, helping us achieve a clear view of image rotation. | 3.The warp affine function, uses the affine transformation defined by the rotation matrix. | 2. This can be achieved in Halide with the help of efficient scheduling methods such as tiling, vectorizing, and unrolling operations that rely on repetitive operations, such as loops.
3. My work lately mostly involves analyzing these aspects and seeing how they fare against existing methods.
Details as of May 31, 2024
Student | SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Implementation of affine transformation without inbuilt function. | Performance Improvements and Thorough comparison in different aspect. | Comparing the performance of various rotation algorithms on Halide and testing the scope of auto-scheduling
| 1. Removed the dependency on the wrap affine transformation function, leading to an efficient implementation. | 1.Conducted a thorough comparison of the time taken to process various images using the original and optimized code. | 1. Upon some observation, it has come to light that most of the times, existing rotation algorithms, running serially, outperform those run on Halide.
| 2. Successfully implemented the affine transformation algorithm from scratch without relying on inbuilt functions. Carefully translated the mathematical formulation of affine transformation into code, ensuring accuracy and efficiency. Gained a comprehensive understanding of each step in the affine transformation process. | 2.Tested the performance with different image sizes and resolutions to ensure comprehensive analysis. Observed significant improvements in processing time with the optimized code across all tested images. Encountered some drawbacks in the optimized code like corners being Trimmed, grey Scale Compatibility. | 2. To better understand the reason and find the possible solution to this, I've been trying out various other algorithms to see which one performs the best, and at the same time leverage Halide's auto-scheduling techniques to optimize the program.
Details as of June 04, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Optimization of affine transformation with Scheduling Techniques. | Compare the time between parallel , vectorized and all Parallel Scheduling technique | Study and analyze the DLR (Double Line Rotation) algorithm for image rotation.
| 1. Successfully optimized the affine transformation using scheduling techniques. | 1. Implemented the affine transformation using three methods: tiling, parallel processing, and vectorization. To evaluate their performance, I compared the following approaches: | 1. The DLR algorithm was studied in an attempt to look back and see which algorithm itself is the "fastest" for rotating images.
| 2.Implementation of scheduling techniques in affine transformations efficiently allocate resources by vectorizing and parallelizing tasks. This optimization ensures that computational resources are used to their full potential, minimizing idle time. This approach significantly reduces computation time, leading to faster execution of tasks and improved performance. | •Combining all three methods: tiling, parallel processing, and vectorization. •Using only parallel processing. •Using only vectorization. | 2. Unlike other image rotation algorithms, which are multi-pass, the DLR algorithm is a single-pass algorithm, which not only makes it easier to implement, but also makes it a lot more accurate than other methods. Issues like anti-aliasing, and image skewing are taken care of all in one single iteration.
Details as of June 07, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Understanding the mathematical concept of rotation of image with Hermite Expansion. | Implement Hermite Expansion in code. | Implement and benchmark the DLR algorithm in code.
| 1. Successfully understand the concept of rotation of image with the help of the hermite Expansion. This allows for efficient manipulation and transformation of the image, including rotation. | 1.Implemented the hermite expansion polynomial in halide. | 1. After studying the paper (Ashtari, Amir Hossein, Md Jan Nordin, and Seyed Mostafa Mousavi Kahaki. "Double line image rotation." IEEE Transactions on Image Processing 24.11 (2015): 3370-3385.), it was found out that a lot the times, the values provided in the paper cannot be used as is, and needs some modifications to be practically usable.
| 2. By the properties of Hermite polynomials, we can achieve an approach of rotation with minimal distortion or loss of information . Each pixel value in the original image is represented as a linear combination of Hermite polynomials. | 2. Implemented the code to find out Sum of the Hermite Polynomial Terms. | 2. After getting an initial prototype working in C++, it was found that the DLR method does indeed best other existing rotation algorithms, albeit by a slight margin.
Details as of June 11, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| 1.Implemented the rotate_image and reconstruct_image function | 1. implemented the 'rotate_hermite' function. | Encountered issues implementing DLR in Halide.
| 2.But got error in the rotate_hermite | 2. However, got an type casting error in the 'hermite_expansion' function. | The current method evaluates pixels in an irregular range, with irregular loop increments. The issue here is that Halide operates on a pretty discrete domain, with regular updates in loop variables, unlike in the method that's currently in use, which not only operates over an irregular domain, but also increments loop variables only when very specific conditions are met.
Details as of June 14, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Implement Hermite function recursively | Implement Hermite Expansion in code. | Use MMX and SSE intrinsics instead of Arm NEON to use compiler intrinsics to achieve optimisation.
| 1. Changed the previous approach to a recursive approach, finding the hermite function recursively. | 1. I have updated the Hermite polynomial function to accept two Expr parameters. | 1. After the Halide implementation leaving us in a deadlock, using compiler intrinsics to achieve optimization instead seemed reasonable.
| 2. But got Hermite Compile error regarding the implicit casting, that's not possible in hermite. | 2. However, this change causes a segmentation fault to occur. | 2. Arm NEON cannot be used as of now, since it's only available for the arm architecture, so as of now, we're looking at MMX and SSE intrinsics instead, which are the x86 equivalents.
Details as of June 17, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Remove the compilation error from the implementation. | Remove the segmentation fault from the code. | Got Arm NEON to work on x86 machines.
| 1. Removed the compilation type casting error from the code, so that the code runs well but not able to find out the output. | 1.Removed the segmentation fault from the code, code runs well but it gets stuck in the realize part. | 1. As previously discussed, since Arm NEON is only available on the arm architecture, the issue was resolved with the help of cross-compilation of dependencies.
| 2. However, not sure that the output will be correct or not. | 2. Tried to debug it by giving print statement after each execution of function. But still not get the overall output. | 2. Now, we can exploit NEON intrinsics to optimize our code, even on an x86 machine.
Details as of June 21, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Compared result of the hermite expansion with the wrapAffine | Implemented Image Rotation using Hermite Expansions | Implemented DLR Algorithm for Zone 2.
| 1. Benchmarked the result of hermite expansion with the OpenCv inbuilt function i.e wrap_affine. | 1.Implemented the hermite Rotation Algorithm using openCV in CPP. | With NEON working now, focus could be shifted to further extending the DLR algorithm.
| 2.The result is quite near to the wrap_affine and the difference is not very much. In some cases hermite is beating up the wrap affine, but not fully. | 2. However, the output image does not have the same color as the original; there are some distortions. | Previously, it was only done for zone 1, i.e. from 0° to 45°, and now it is being extended to zone 2, i.e. 45° to 90°. There have been some implementation issues, but time will be spent debugging the same.
Details as of June 25, 2024
| SUBHADEEP BHADRA | SOURAV KUMAR PARIDA | DHRUBAJYOTI MANDAL
| Understanding the Mathematical concept of Bresenham. | Implementation of Bresenham algorithm to rotate a image. | Benchmarked the DLR algorithm.
| Discussing about this technique in computer graphics for drawing lines and other shapes on a pixel grid. It efficiently determines the points that need to be plotted to form a close approximation to a straight line between two points. | Line Drawing: Implemented Bresenham's algorithm to efficiently generate points of a line between two coordinates using integer arithmetic, ensuring accurate and fast line rendering. | Comparing the performance of the DLR algorithm to the benchmark - the built-in implementation of image rotation in OpenCV, which uses the warpAffine function, it is seen that DLR beats the benchmark for smaller images, and starts to fall behind for images exceeing a resolution of 1080p.
| When it comes to image rotation, Bresenham's algorithm can be adapted to help determine which pixels in the original image map to which pixels in the rotated image | Image Rotation: Created a custom image rotation function leveraging Bresenham's line algorithm to scan lines, apply rotation transformations, and fill gaps using nearest-neighbor interpolation. | The reason for such a high performance in the benchmark is supposedly the fact that it actually uses multithreading in the background. As such, implementing any further in the DLR algorithm would involve using multithreading or other forms of parallelism as well.